MVP Roadmap and Juba Pilot Plan

Digital Group Savings, Rotating Payouts, and Group-Backed Loans for Juba

Version 1.0 | May 2, 2026

# 1. Roadmap Philosophy

The product should be built in a practical sequence. Start by proving that groups will trust the app for records, rules, contributions, loans, and payouts. Do not begin by holding real funds or promising automatic payment integrations before provider partnerships exist.

# 2. MVP Scope

Mobile app for members, admins, and treasurers.

Group creation and digital constitution.

Member invites and role assignment.

Contribution schedule and manual payment proof upload.

Treasurer confirmation and ledger posting.

Group wallet and individual wallet ledger views.

Fixed payout order and payout receipts.

Loan request, eligibility checks, approvals, guarantors, repayments, and penalties.

Basic reporting and export.

Platform admin tools for support and audit review.

# 3. Build Phases

| Phase | Duration | Deliverables |
| --- | --- | --- |
| Phase 0: Discovery | 1-2 weeks | Interview groups, confirm common rules, choose name, design prototype. |
| Phase 1: Core app foundation | 2-3 weeks | Auth, profiles, groups, roles, invites, basic dashboard. |
| Phase 2: Contributions and wallets | 3-4 weeks | Contribution schedules, payment proof, treasurer confirmation, group/member ledgers. |
| Phase 3: Payouts | 2 weeks | Payout order, payout summary, deductions, multi-approval, receipts. |
| Phase 4: Loans | 3-4 weeks | Eligibility, max loan rules, guarantors, approvals, repayment, default workflow. |
| Phase 5: Pilot polish | 2 weeks | Reports, notifications, support tools, bug fixes, UAT. |

# 4. Suggested 12-Week MVP Timeline

| Week | Focus | Outcome |
| --- | --- | --- |
| 1 | Discovery and rule collection | Document 5-10 real savings group patterns in Juba. |
| 2 | UX prototype | Clickable prototype and user flow tested with 2-3 group leaders. |
| 3 | Backend setup | Database, auth, roles, base API. |
| 4 | Mobile app foundation | Login, profile, group creation, invites. |
| 5 | Contribution engine | Schedules, due dates, payment proof upload. |
| 6 | Treasurer workflow | Payment confirmation, ledger posting, receipts. |
| 7 | Wallet dashboards | Group wallet, member wallet, transaction history. |
| 8 | Payout engine | Payout order, deductions, payout approvals. |
| 9 | Loan engine | Loan request, eligibility, limits, terms display. |
| 10 | Guarantors and repayments | Guarantor acceptance, repayment tracking, overdue handling. |
| 11 | Reports and notifications | Statements, reminders, admin support view. |
| 12 | Pilot launch readiness | UAT, fixes, training materials, pilot onboarding. |

# 5. Pilot Design

Start with 3 to 5 groups. Each group should have 5 to 15 members, a known leader, and existing savings behavior. The pilot should use real behavior but conservative controls. For legal and trust safety, real money should be held by the group account, not by the app owner.

| Pilot Parameter | Recommendation |
| --- | --- |
| Number of groups | 3-5 groups |
| Members per group | 5-15 members |
| Cycle duration | 4 weeks |
| Contribution frequency | Weekly first; daily later |
| Currency | SSP first, USD optional if pilot group requires it |
| Loan limit | 50% of expected payout or lower |
| Money custody | Group-controlled bank/mobile money account |
| Support | WhatsApp support group plus in-app support tickets |

# 6. Pilot Onboarding Script

Meet group leadership and explain the app as a transparency and record-keeping tool.

Confirm group rules in writing: contribution amount, frequency, payout order, loan rules, penalties, approvals.

Create the group in the app and assign admin, treasurer, and secretary/auditor roles.

Invite members and help them complete profile setup.

Ask each member to accept the digital constitution.

Run one test contribution with small amount or demo mode.

Begin the first real cycle only after all members understand the process.

Collect feedback weekly and document issues.

# 7. Go-To-Market for Juba

| Channel | Approach |
| --- | --- |
| Market groups | Partner with trusted market leaders and demonstrate contribution tracking. |
| Salons and boutiques | Use women-led savings circles as early ambassadors. |
| NGO/workplace groups | Present as a staff welfare/savings transparency tool. |
| Church/community groups | Emphasize trust, receipts, and group accountability. |
| Social media | Short videos explaining “who paid, who receives, who borrowed”. |
| Referral program | Give free first cycle or discounted month for groups referred by existing groups. |

# 8. Launch Metrics

At least 3 pilot groups complete one full cycle.

At least 90% of scheduled contributions are recorded correctly.

At least 95% of members understand their wallet balance and payout order.

No unresolved payout dispute at the end of pilot cycle.

At least 2 groups agree to continue using the app after pilot.

Support issues are documented and converted into product fixes.

# 9. Post-Pilot Decisions

Whether to keep ledger-first model or pursue payment integration immediately.

Which payment providers or banks to approach first.

Whether to add SMS/USSD fallback.

Whether daily contribution groups need agent-assisted confirmation.

Whether loan functionality should remain conservative or expand.

# Reference Notes and Sources

These references were used only to shape the regulatory and market context. This document is not legal advice. Before handling real funds, consult a South Sudan-qualified legal adviser and engage the Bank of South Sudan or a licensed financial institution.

Bank of South Sudan - National Payment System overview: https://boss.gov.ss/national-payment-system/

Bank of South Sudan - acceptance of mobile money as legal tender/public notice, 2025: https://boss.gov.ss/wp-content/uploads/2025/07/legal.pdf

Bank of South Sudan - functions as operator and regulator of the NPS; e-money licensing/trust account references, 2025: https://boss.gov.ss/wp-content/uploads/2025/09/functions-of-the-bank-of-south-Sudan-as-operator-and-Regulator-of-the-NPS-in-South-sudan_0001.pdf

UNDP South Sudan - Digital Mobile Wallet Usage as an Enabler for Financial Inclusion, 2025: https://www.undp.org/south-sudan/publications/digital-mobile-wallet-usage-enabler-financial-inclusion-undp-south-sudan-report

UNCDF - South Sudan Policy Diagnostic Report, 2023: https://migrantmoney.uncdf.org/wp-content/uploads/2023/11/South-Sudan-Diagnostic-Report.pdf